## Weekly Log
IT9201 – Machine Learning and Data Mining ¦ Project Weekly Log
Project Name: | Predicting Gen Z Purchase Intention Through AI-Powered Digital Marketing Campaigns Using Machine Learning Techniques
Student Name: | Manal Talal Ameen
Student ID: | 12011218
Course: | Machine Learning and Data Mining: IT9201 Project
Submission: | 31 May 2026 ¦ Log updated every Saturday at 11:59 pm
Date | Week No | Task Name | Work Done During the Week (Bullet Points / Description) | Issues Experienced
26 Apr 2026 | 1 | Task 1: Problem Definition & Literature Setup | • Read project brief and instructions for assessment IT9201 • Determined the research topic: “Gen Z purchase intention through ML” in Alsaadi et al. (2024) dataset • Extracted the dataset from GitHub (github.com/Hana0111/Digital-Marketing) • The section "Problem Definition" has been drafted as well as the section "Objectives". • Literature Search: Started searching literature with Perplexity AI and identified 6 key references [1][7] | Difficulty accessing Krikheli (2024) paper - obtained through university library portal.
3 May 2026 | 2 | Task 1: Literature Review & Software Setup | • Completed Section 1.3 Literature Review covering references [1][7] • Install Google Colab with Python 3.x, pandas, NumPy, scikit-learn, Matplotlib and Seaborn. • Loaded dataset; ran df.shape and df.head() and it showed 520 rows, 49 columns • Detected 0 missing values in each column • Prepared Section 1.4 Software Libraries and created Table 1 | Column names had leading/trailing spaces causing KeyError - fixed with df.columns.str.strip().
10 May 2026 | 3 | Task 2: Dataset Description, EDA & Preprocessing | • Completed Section 2.1 Dataset Description with Table 2 (variable categories) • Performed EDA: class distribution — 259 Positive (49.8%), 143 Negative (27.5%), 118 Neutral (22.7%) • Created Figure 1 (class distribution bar chart) and Figure 2 (all 48 features importance) • RF pre-analysis on all 48 features was performed and top 7 predictors were identified. • Created Figure 3 (correlation heat map) and Table 3 (descriptive statistics) Performed Data Preprocessing – Section 2.3 (Table 4) – 80/20 train-test split | No issues - dataset was clean with zero missing values, simplifying the preprocessing pipeline.
17 May 2026 | 4 | Task 2 & 3: ML Framework, Feature Selection & Model Training | • Wrote Sections 2.4 (How ML was Applied) and 2.5 (Proposed ML Framework - Table 5, Figure 5) • Completed 7-feature selection; reasons for importances in Table 6 Trained Logistic Regression: Accuracy: 52.88%, Macro F1: 39.15% (Figure 6) • Trained Decision Tree: Accuracy 54.81%, Macro F1 48.22% (Figure 7) • Trained Random Forest (default): Accuracy 51.92%, Macro F1 47.45% (Figure 8) • Produced a chart that compares the models (Figure 12) | LR failed entirely on Neutral class (F1=0.00) - confirmed dataset is not linearly separable; documented as key finding.
24 May 2026 | 5 | Task 3 & 4: Evaluation, Orange Validation & Hyperparameter Tuning | • Identified and recorded evaluation metrics in Table 7 and full outcomes in Tables 8 & 9 Orange 3: no-code replication – 5-fold CV on all 3 classifiers (Table 10, Figure 14) • Ran GridSearchCV on RF: n_estimators=[50,100], max_depth=[5,10], cv=3, scoring=f1_macro • Best params: n_estimators=100, max_depth=5 — Best CV Macro F1: 60.37% (Table 12, Figure 13) • Produced Figure 9 (optimised RF feature importance) and Figure 11 (confusion matrix) • Applied K-Means (k=3, n_init=10) — 3 behavioural segments identified (Table 14, Figures 15 & 16) | CV F1 (60.37%) vs test F1 (45.89%) gap larger than expected - investigated and documented as typical variance at this sample size.
25 May 2026 | 6 | Task 5: Discussion, Report Finalisation & Submission | • Wrote Task 5: Summary of Findings, Critical Analysis, Comparison to Prior Work, Future Extensions • Checked all figure/table numbering and cross-references in report • Wrote fully annotated Python code for Appendix A • Uploaded Jupyter Notebook, data (CSV), and all figures to GitHub repository. • Final editing of work, formatting; submission of report on Moodle before deadline | Minor figure numbering inconsistency (Figure 4 vs Figure 5 labelling) detected and corrected before submission.